## Budget
The project budget
Phase |  | Responsible | Material resources | Cost | Total
1.- Initiation
| 1.1.- Initial act | Project manager | Computer, microsoft office package, pen, sheets, transport, printer, ink, light, table, chair | 974.61 | 30292.63
2.- Planning
| 2.1.- Budget worksheet | Project manager | Chair, computer, microsoft office package, table, light | 949.17
| 2.2.- Deliverables | Project manager | Computer, light, chair, microsoft office package, table | 949.17
| 2.3.- Milestones | Project manager | Computer, light, chair, table, microsoft office package | 949.17
| 2.4.- WBS | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32
| 2.5.- Communication Plan | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32
| 2.6.- Tool for Quality Management | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32
| 2.7.- Scope Statement | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32
| 2.8.- Life Cycle selection | Project manager | Computer, internet and telephone service, light, chair, table, | 944.62
3.- Analysis
| 3.1.- Evaluate suppliers | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
| 3.2.- Selection of data collection technique | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
| 3.3.- Interview | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
| 3.4.- Functional requirements | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
| 3.5.- Non-functional requirements | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
| 3.6.- SRS | Analyst | Chair, computer, microsoft office package, table, internet and telephone service, light | 857.32
4.- Design
| 4.1.- Entity-Relation diagram | Designer | Pen, computer, sheets, chair, table | 776.28
| 4.2.- Relational Diagram | Designer | Computer, pen, sheets, chair, table, SGBD | 773.28
| 4.3.- Navigation Map | Designer | Computer, light, chair, table | 780.47
| 4.4.- Layout | Designer | Computer, chair, light, table, adobe packages | 792.27
5.- Development
| 5.1.- Database | Programmer 2 | Computer, light, chair, internet and telephone service, table, SGBD | 792.62
| 5.2.- Layout | Programmer 1 | Chair, computer, internet and telephone service, table, adobe package | 796.65
| 5.3.- Página Conócenos | Programmer 3 | Computer, internet and telephone service, light, chair, table, IDE | 792.62
| 5.4.- Página Productos | Programmer 3 | Computer, internet and telephone service, light, chair, table, IDE | 792.62
| 5.5.- Página Platillos | Programmer 1 | Computer, internet and telephone service, light, chair, table, IDE | 792.62
| 5.6.- Página Pedidos | Programmer 2 | Computer, internet and telephone service, light, chair, table, IDE | 792.62
| 5.7.- Página Index | Programmer 1 | Computer, internet and telephone service, light, chair, table, IDE | 792.62
6.- Tests
| 6.1.- Unit tests | Tester | Computer, internet and telephone service, light, chair, table,IDE | 792.62
| 6.2.- Module tests | Tester | Computer, internet and telephone service, light, chair, table,IDE | 792.62
7.- Implementation
| 7.1.- Hosting selection | Designer | Computer, internet and telephone service, light, chair, microsoft office package, table | 809.32
| 7.2.- Upload the application | Designer | Computer, internet and telephone service, light, chair, table | 792.62
| 7.3.- System tests | Tester | Computer, internet and telephone service, light, chair, table | 792.62
8.- Project closure
| 8.1.- Acceptance letter | Project manager | Pen, sheets, transport, chair, computer, ink, internet and telephone service, microsoft office package | 979.79
| 8.2.- Project closing act | Project manager | Pen, sheets, transport, chair, computer, ink, internet and telephone service, microsoft office package | 979.79
| 8.3.- Lessons learned checklist | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32
| 8.4.- Lessons learned document | Project manager | Computer, light, chair, internet and telephone service, microsoft office package, table | 961.32

## Resources
Material
Name | Cost
Project Manager | $113.00/h
Analyst | $100.00/h
Designer | $94.00/h
Programmer 1 | $94.00/h
Programmer 2 | $94.00/h
Programmer 3 | $94.00/h
Tester | $94.00/h
Pen | 3.5
Notebook | 0.12
Computer (Wastage) | 13.7
Sheets | 0.08
Printer | 8.9
Internet and telephony service | 12.15
Light | 7.77
Chair (Wastage) | 4
Table (Wastage) | 4
Transport | 20
Soap | 1.8
Ink | 6.66
Water service | 0.66
Toilet paper | 0.83
Drinking water | 3.5
Fan (Wastage) | 0.41
Telephone | 0.69
Microsoft Office Package | 16.7
Adobe package | 11.8
SGBD | 0
IDE | 0